## Cover Page
163-Vehicle Reservation System
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Aravinthan P
Role
Signature
Date
Project ID: Car Servicing | HYD19IJ003 |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog 163-Vehicle Reservation System Project ID: HYD19IJ003 C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
FS1 | Task 1 | Requirement and analysis. | Aravinthan | 1 | 2 | [5 empty] | Completed
FS1 | Task 2 | Screen should display the option for Admin login / Registration and Member login / Registration. | Aravinthan | 2 | 2 | [5 empty] | Completed
FS1 | Task 3 | Create A database table toStore User and vehicle details/Create a java class to perform database operations on User registration. | Aravinthan | 3 | 3 | [5 empty] | Completed
FS1 | Task 4 | When the Member clicks on the registration link,it should re-direct to registration form and able to fill required information with validation. | Aravinthan | 2 | 2
FS1 | Task 5 | Admin/Member able to register and login with proper validation. And save information to database. And admin can able to aprove and deny user request. | Aravinthan | 4 | 2 |  |  |  | 2 |  | Completed
FS1 | Task 6 | Admin/Member should abel to view all vehicles. Member registration approval on that basis member login. | Aravinthan | 4 |  | 3 |  |  | 1 |  | Completed
FS2 | Task 1 | Admin on successful login should have option to add new vehicles. And on successful login admin and user should be able to view vechile details. | Aravinthan | 5 |  | 5 |  |  |  |  | Completed
FS2 | Task 2 | The view should have the filter and sort option. Filter should have different category as vehicle type, status, 4 seater/6 seater etc. | Aravinthan | 2 | [6 empty] | Completed
FS2 | Task 3 | On selecting the vehicle, the vehicle details page should open which should list all the details of the vehicle and Search option should be available for admin/user and search based on vehicle number. | Aravinthan | 4 |  | 1 | 4 |  |  | 2 | Completed
FS2 | Task 4 | Admin should have an option to edit the Vehicle details and bale to delete any vehicle details. And Vehicle details shouldn’t be editable for User. | Aravinthan | 4 |  |  | 3 |  | 1 |  | Completed
FS2 | Task 5 | User on clicking the Book Vehicle option, User should be prompted to enter the number of days the vehicle should be reserved. And on that basis bill will generate. | Aravinthan | 6 |  |  | 3 | 3 | 2 | 3 | Completed
FS3 | Task 1 | User should have different option to pay. | Aravinthan | 3 |  |  |  | 2 | 1 |  | In-Progress
FS3 | Task 2 | On Successful payment, booking should be confirmed and the vehicle status should be updated automatically. | Aravinthan | 4 |  |  |  | 2 | 2 | 3 | Completed
FS3 | Task 3 | On Successful payment, booking should be confirmed and the vehicle status should be updated automatically. | Aravinthan | 2 | [5 empty] | 2 | Completed
|  | Total |  | 46 | 11 | 9 | 10 | 7 | 9 | 10
Sprint Goal
Some sprint goal

## Sprint 2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
|  | Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
Some sprint goal

## Data (hidden)
In-Progress
Completed
N/A